MindCare

B2B2C Counselling & Wellness Platform

Revised Platform Plan

Version 2.0 | March 2026

Client: Indic Labs

Prototype Deadline: 1st Week of April 2026

Platforms: Web App + Android App

# Table of Contents

# Executive Summary

MindCare is transitioning from a B2C to a B2B2C model, partnering with schools and corporates to provide counselling and wellness services. Organizations receive unique codes for their members, who get free credits for consultations. This document outlines the complete platform architecture, user flows, and implementation timeline.

# Platform Mind Map

The following mind map provides a visual overview of the MindCare platform architecture, showing the relationships between key components:

# Business Model Evolution

## Previous Model (v1) — B2C

- Individual users sign up directly

- Take self-assessments

- Browse and connect with counsellors

## New Model (v2) — B2B2C

- MindCare partners with Schools & Corporates

- Each organization gets a unique code (e.g., DELHI-PUBLIC-2026)

- Students/Employees join using their organization code

- Members receive FREE credits for consultations

- Teachers log student behavior & flag counseling needs

- HR monitors employee wellness trends

# User Roles

The platform supports seven distinct user roles, each with specific permissions and responsibilities:

| Role | Who | Responsibilities |
| --- | --- | --- |
| Super Admin | MindCare Team | Manage everything — organizations, counsellors, billing, platform |
| Org Admin | Principal / HR Head | Manage their org — invite users, view reports, assign assessments |
| Teacher | School Teacher | Log student behavior, flag students for counseling, view class wellness |
| HR Manager | Corporate HR | View employee wellness trends, assign assessments, manage credits |
| Student | School Student | Take assessments, breathing exercises, book counseling (free credits) |
| Employee | Corporate Employee | Same as student but in corporate context |
| Counsellor | In-house or External | Manage availability, conduct sessions, write notes |

# Platform Architecture

The MindCare platform consists of three client applications sharing a unified backend:

### Client Applications

- Web App — For Students, Employees, Teachers, and Counsellors

- Android App — For Students and Employees (mobile-first experience)

- Admin Dashboard — For Super Admins and Org Admins

### Backend Stack

- REST API built with Node.js and Express

- MySQL database with Prisma ORM

- JWT-based authentication

- Hosted on Oracle Cloud (free tier)

# Application Flows

## Onboarding Flow

- User opens app

- Enter Organization Code (e.g., DELHI-PUBLIC-2026)

- App validates code and displays organization name + logo

- Login (existing users) or Register (new users)

- Redirect to role-based dashboard

## Student / Employee Flow

Dashboard Features:

- Mood Check-in — Daily emoji-based mood tracking

- Self Assessments — Assigned (mandatory) and free (optional)

- Breathing Exercises — Animated guided sessions

- Theory Sessions — Educational modules with progress tracking

- Book Consultation — Browse counsellors, pick slots, book with credits

- Credits Balance — "5 free sessions remaining"

## Teacher Flow

Dashboard Features:

- My Classes — View assigned classes and sections

- Student Directory — All students in assigned classes

- Behavior Log — Log entries with date, category, notes, severity

  - Categories: Academic, Social, Emotional, Behavioral

  - Severity: Low, Moderate, High, Critical

- Flag for Counseling — Triggers notification to counsellor and admin

- Class Wellness Overview — Mood scores, assessment completion, flagged students

## HR Manager Flow

- Employee Wellness Overview — Department-wise scores and trends

- Assign Assessments — Select department, choose assessment, set deadline

- Credit Management — View allocation, usage, and request more

- Reports — Downloadable CSV/PDF exports

## Counsellor Flow

- Today's Schedule — View upcoming sessions

- My Clients — View history, assessments, behavior logs

- Availability Management — Set weekly schedule, block dates, session duration

- Flagged Students — Review behavior logs, schedule consultations

- Session Notes — Private notes per session, summary visible with consent

# Credit System

## Credit Packages

| Package | Sessions | Price |
| --- | --- | --- |
| Starter | 50 sessions | ₹25,000 |
| Growth | 200 sessions | ₹80,000 |
| Enterprise | 500 sessions | ₹1,50,000 |

## Credit Distribution Models

- Equal Distribution — 5 credits per student/employee

- Custom Allocation — HR/Admin allocates individually

- Shared Pool — Organization pool, first-come first-served

## Booking Flow

- User initiates booking

- System checks: Does user have credits OR does org pool have credits?

- If YES: Book session, deduct 1 credit

- If NO: Display "No credits available. Contact your admin."

# Database Schema

## New Models

### Organization

- id, name, type (SCHOOL/CORPORATE), code (unique)

- logo, address, contactEmail, contactPhone

- creditBalance, status, createdAt

### OrganizationMember

- id, userId, organizationId

- role (STUDENT/EMPLOYEE/TEACHER/HR/ORG_ADMIN)

- class/department, creditBalance, joinedAt

### Consultation

- id, userId, counsellorId, organizationId

- slotDate, slotTime, duration, type (IN_PERSON/VIDEO)

- status (BOOKED/COMPLETED/CANCELLED/NO_SHOW)

- creditUsed, notes (private), summary (shareable)

### BehaviorLog

- id, studentId, teacherId, organizationId

- date, category (ACADEMIC/SOCIAL/EMOTIONAL/BEHAVIORAL)

- severity (LOW/MODERATE/HIGH/CRITICAL)

- notes, flagForCounseling, counselingStatus

# Implementation Timeline

10-day sprint from March 23 to April 1, 2026

| Day | Tasks |
| --- | --- |
| Day 1 | Foundation — Organization model, org code validation, update auth flow |
| Day 2 | Roles & Members — OrganizationMember model, role-based middleware, user management |
| Day 3 | Credits & Availability — Credit system, ConsultationSlot model, counsellor schedule |
| Day 4 | Consultation Booking — Booking API, consultation management, user booking page |
| Day 5 | Teacher Features — BehaviorLog model, teacher dashboard, flag for counseling flow |
| Day 6 | Assignments — Assignment model, admin assignment UI, student view |
| Day 7 | Analytics & Reports — Org-level analytics, wellness charts, CSV export |
| Day 8 | Integration & Polish — End-to-end flow, navigation, error handling |
| Day 9 | Testing & Fixes — E2E testing, bug fixes, demo data seeding |
| Day 10 | Prototype Ready — Final testing, deploy to Oracle Cloud, share with client |

# Reuse Scorecard

Approximately 75% of existing code is directly reusable for the new B2B2C model:

| Component | Reuse % | Changes |
| --- | --- | --- |
| Express API + Prisma + JWT auth | 100% | Add org middleware |
| Breathing exercises (animated) | 100% | Zero changes |
| Theory sessions + progress | 95% | Add assignment link |
| Assessment quiz flow | 90% | Add assignment flag |
| Counsellor list + detail | 80% | Add availability + booking |
| User management | 80% | Scope to org |
| Admin dashboard | 70% | Org-scoped + role-based |
| Android app (6 screens) | 70% | Add org code + booking |
| Dark/light mode + design system | 100% | Zero changes |
| Rate limiting + security | 100% | Zero changes |

# Phase 2 Features (Post-Prototype)

The following features are planned for Phase 2, after prototype validation:

| Feature | Reason for Deferral |
| --- | --- |
| Video call integration (Zoom/Meet) | Complex integration; use join link for now |
| Payment gateway | Manual billing sufficient for prototype |
| iOS app | Android first for market validation |
| Push notifications | Requires Play Store submission |
| Counsellor rating/review | Needs real session data |
| Multi-language support | English first for prototype |
| Custom branding per org | After MVP validation |
| Detailed treatment plans | Pending counsellor feedback |

# Risk Assessment

| Risk | Impact | Mitigation |
| --- | --- | --- |
| 10 days is tight for all features | High | Prioritize booking + org code for demo |
| Counsellor availability is complex | Medium | Start with simple time slots, no recurring |
| Credit system edge cases | Medium | Keep it simple — 1 credit = 1 session |
| Role-based access (7 roles) | Medium | Start with 4 core roles for prototype |
| Android changes needed | Low | Update login flow + add booking screen only |

Summary Old app: Individual users → assessments + breathing New app: Organizations → students/employees → full wellness platform Reuse: ~75% of existing code Timeline: 10 days to working prototype Cost: ₹0/month hosting (Oracle free tier) + ₹2,100 Play Store